Minutes for Committee Members Meeting

Date:	November 5, 2015
Time:	12:30 PM CDT

Means:	Conference Call

Attendees:	Ahmet Erdemir
Bill Lytton
Marc Horner
Lealem Mulugeta

Not Available:	Jerry Myers
Lu Tian
Gary An
Tina Morrison
Joy Ku

Agenda:

1. Marc Horner (new Committee member) introduction – 5 min.
2. Update on new member recruitment - 5 min
3. Ten Simple Rules publication & survey analysis update - 5 min
4. New initiative on documentation of M&S workflows - 5 min
5. Recap of action items from previous meeting - 5 min
6. Other – 5 min

Action Items:

See Notes for details.

- Marc:
  - Get a SimTk account with a photo, and upload a brief bio and his photo to the CPMS wiki page.
  - Work with Lealem to identify areas of overlap between V&V40 and CPMS
- Lealem:
  - Send out the link to the IMAG/MSM Meeting presentation, which includes preliminary results of the survey.
  - Send out the link to the current draft of the manuscript.
  - Start a forum discussion on the interpretation of survey results.
  - Update web/wiki pages of the Committee mentioned in the final Avicenna roadmap document.
  - Move Jim Thomas to past members
  - Email committee to get input on how to move forward regarding Alison Marsden
- Ahmet:
  - Add Marc to the CPMS team member list
  - Reach out to Sylvia (from MSM??) regarding available Executive spot
  - Reach out to Susan (previously from NIH working in behavioral and population modeling, now at U. Indiana) regarding available Advisory Council spots
  - Reach out to the rest of the MSM community to get feedback on the workflow development and sharing effort that was recently initiated by Tony Hunt
- Lealem & Ahmet:
  - Reach out to various candidates for open Advisory Council posts.
- Gary:
  - Reach out to Markus Reiterer and Carol Herman again
  - Follow up with the Geo modeling community.
  - Gary will send the group the link for the final Avicenna roadmap.
- Joy:
  - Reach out the Alison for further discussions of Committee activities.
- Data Analysis Group:
  - Start meeting regularly for interpretation of survey results.
Notes:

Marc Horner (new Committee member) introduction.
  - Chemical engineering PhD, joined fluent as a CFD engineer. When ANSYS acquired fluent, his position changed to help advance the use of M&S in medial domain. He has been involved with regulatory issues for some time since he has been with Ansys, and he has been actively involved in the development of the ASME V&V40 standard for application of M&S to medial devices. Through these efforts, he has developed many collaborations with the FDA, universities and industry players.
Update on new member recruitments
  - Majec Swat – Interested but recently found a new job, so until he is settled into his new role
  - Alison Marsden – she is interested in being an executive member, but is not able to do more than one year. We will discuss on her candidacy at the next Executive meeting, or Lealem will send out an email to weigh our options.
  - Ahmet will follow up with potential candidates listed in his action items list
Ten Simple Rules.
  - Lealem will contact the Data Analysis Group members to establish regular occurring meetings. Preferably starting in November.
  - Marc asked about the scope and purpose of the TSR initiative. Lealem directed Marc to review the documents he was initially emailed to get an overview of the work. Part of these documents includes two presentations that summarize the current results and links to a poster Ahmet prepared to summarize the outcome of the committee's perspectives on the Ten Simple Rules of Credible Practice of M&S in Healthcare.
New initiative on documentation of M&S workflows
  - One of the Committee's charges is to develop and demonstrate workflows of credible practice. With that in mind, Tony Hunt (AC member) initiated a conversation with Ahmet and Lealem to share and discuss the workflows used by different disciplines. As an outcome of these discussions, several documents were generated that demonstrate workflows that have been developed and successfully used by them.
  - Lealem initiated an forum discussion to make the discussions more public and all committee members are encouraged to participate: https://simtk.org/forums/viewtopic.php?f=848&t=6044&sid=9971ea6893a9a5cd8a59d659e8780fc4
  - Tony has sent out an email to Systems Biology working group with the documents attached to get further contributions on the subject.
  - Lealem also sent out an email to the committee membership to get further feedback
  - Ahmet will send an e-mail to reach out to whole MSM community.
  - These discussions were also a good to remind us that the subtlety of the language we all use in our unique areas of M&S can sometimes confuse things. Therefore, the Glossary initiative needs to be revitalized.
Recap of action items from previous meeting
  - Ahmet posted the IMAG/MSM breakout meeting minutes: https://simtk.org/websvn/wsvn/cpms/doc/minutes/msm_20150908.pdf
  - Lealem – started the forum discussion data analysis for Ten Simple Rules initiative: https://simtk.org/forums/viewtopic.php?f=848&t=5616
  - We are still waiting on Gary to get back to us regarding Markus Reiterer and Carol Herman, Geo simulation contacts
  - Gary emailed the Committee the Avicenna website and roadmap:
    - Website: http://avicenna-isct.org/
    - The Roadmap is here http://avicenna-isct.org/roadmap/
    - Committee is mentioned on:
      - Page 69 - Footnote 86: http://www.imagwiki.nibib.nih.gov/content/committee-credible-practice-modeling-simulation-healthcare-description
      - Page 70 - Footnote 87: http://wiki.simtk.org/cpms/Ten_Simple_Rules_of_Credible_Practice
  - Joy reached out to Alison Marsden – see summary notes of item #2 for status
Other Business.
  - Tina Morrison sent out a reminder regarding the FDA/BMES Frontiers in Medical Devices conference. Marc reached out to conference chairs to point out how M&S credibility is growing as an important topic, and how it may be worth including as part of the conference. If the organizers see value in this, Marc suggested to connect the Committee with the organizers to advance this idea further.
  - Ahmet suggested submitting an abstract to discuss the current results of the community survey and comparison to the committee perspective results.
  - Marc suggested a compare and contrast the works of CPMS and V&V40 to show where we overlap and differ, and the overall value of both efforts. Marc & Lealem will get together to work on this in readiness for preparing an abstract to submit to the conference.