(1) Major activities.
The budget period for this report was 07/01/2018 – 06/30/2019. In this budget year, major activities of the project initially focused on the delivery of Model Development specifications. In following, all collaborating teams (4 national, 1 international) have developed knee models and are conducting sample simulation scenarios. The outcomes, including models, intermediate and final model components, simulation results, protocol deviations, and so on, are being packaged by individual teams and will be disseminated early in the next reporting period. The teams also focused on outreach and scholarly publications, which are summarized below.
(2) Specific objectives.
The overall goal of the project is to understand how modelers’ choices to build models, even when using the same data, may influence predictions and therefore the reproducibility of simulation results. Specific aims are i) to quantify the influence of variations in modeling and simulation workflows on the reproducibility of joint level predictions in computational knee biomechanics, and ii) to quantify the influence of variations in modeling and simulation workflows on the reproducibility of tissue level predictions in computational knee biomechanics. The modeling and development activities in the project are staged to include Model Development, Model Calibration, Model Benchmarking, and Model Reuse.
The primary aim of the reporting period for all teams (Cleveland Clinic, Cleveland State University, University of Denver, Auckland Bioengineering Institute, Hospital for Special Surgery) was to deliver, and in following execute, specifications (protocols) for Model Development phase.
(3) Significant results, including major findings, developments, or conclusions.
All teams submitted their individual workflows (specifications) for development of knee models. These documents were disseminated publicly at the project site, in the “Documents” section [1]. Leveraging the data earmarked for the model development phase (see “Downloads” of project site [1]), each team built models, one for specimen from Natural Knee Data and another for specimen from Open Knee(s). At the moment, the teams are packaging the deliverables of the Model Development phase for dissemination. Investigators also planned a milestone meeting for June 2019 at the University of Denver (a collaboration site) to discuss the results of the Model Development phase.
Instructions on the Model Calibration phase were disseminated to each team and the public on the project wiki [2]. Data earmarked for the Model Calibration phase were also decided upon and disseminated publicly at the project site for teams to utilize [1]. The investigators decided to postpone development and submission of Model Calibration specifications to focus on finalizing the Model Development stage.
Overall, a significant outcome is the public availability of five independent and detailed model development protocols, which are leveraging the same data. These can be considered as data points for science of science, i.e., to understand the art of modeling and simulation. A quick look at these documents already indicate the large variety of choices made by the modelers and the tools they use [3]. Their impact on simulation results and conclusions derived from these is yet to be seen.
(4) Key outcomes or other achievements.
The overall strategy of the project to understand art of modeling and simulation and reproducibility potential of modeling studies has been published in the Journal of Biomechanical Engineering as an invited article [3]. Co-authors (representatives of collaborating teams and Tina Morrison of the U.S. FDA) summarized ongoing and planned activities, leveraged publicly disseminated Model Development specifications to demonstrate variability in approaches, and emphasized the potential impact of the study for the discipline of computational biomechanics.
Investigators will also be organizing a session on art of modeling and simulation in biomechanics at the 16th International Symposium on Computer Methods in Biomechanics and Biomedical Engineering to be held in New York, NY in August 2019. Three teams (Cleveland Clinic, Cleveland State University and Hospital for Special Surgery) submitted studies describing their decision making processes for development of knee models. Dr. Halloran will be presenting about documentation for reproducibility; Dr. Erdemir will focus on understanding subjective decisions, and Dr. Imhauser will elaborate on the identification of anatomical boundaries.
Outreach activities have been impactful to promote awareness to the art of and reproducibility in modeling and simulation of the knee. Dr. Halloran, team leader at the Cleveland State University, gave an invited presentation at VPH 2018 [4] to promote the project in the European Community and build a network with fellow modelers. This resulted interactions with Nico Verdonschot, PhD at Radboud University Medical Center in the Netherlands.
Dr. Imhauser, team leader at the Hospital for Special Surgery, organized a well received workshop on reproducibility in the annual meeting of the Orthopaedic Research Society [5]. Multiple presentations on the topic were provided by Dr. Imhauser (Hospital for Special Surgery, academic perspective), Dr. Cheryl Liu (Stryker, industry perspective) and Dr. Andy Baumann (U.S. FDA, regulatory perspective). Flash opinions by thought leaders in the area of knee modeling were also provided: Dr. Nico Verdonschot from Radboud University Medical Center, Dr. B. J. Fregly from Rice University, and Dr. Jeff Bischoff from Zimmer-Biomet. A lively panel discussion followed. More than 100 participants attended to the workshop. Feedback from participants were received through a short survey. The organizers have been invited by the Editor in Chief, Journal of Orthopaedic Research to write a review based on this workshop. This manuscript will summarize perspectives of the speakers and panelists and synthesize the feedback received from the community.

References
1. Project website @ SimTK: Reproducibility in simulation-based prediction of natural knee mechanics: Project Home, https://simtk.org/projects/kneehub. Accessed on May 15, 2019.
2. Project wiki @ FrontPage – kneehub, https://simtk.org/plugins/moinmoin/kneehub/. Accessed on May 15, 2019.
3. Erdemir, A., Besier, T. F., Halloran, J. P., Imhauser, C., Laz, P. J., Morrison, T. and Shelburne, K. B. (2019) Deciphering the “art” in modeling and simulation of the knee joint: overall strategy, Journal of Biomechanical Engineering, doi: 10.1115/1.4043346. Preprint @ https://simtk.org/svn/kneehub/doc/JBME-2019ASI/JBME-Perspective.pdf. Accessed on May 15, 2019.
4. Halloran, J., Besier, T., Imhauser, C., Laz, P., Morrison, T., Shelburne, K. and Erdemir, A. Collaborative strategy to establish reproducibility in simulation‐based prediction of natural knee mechanics, Virtual Physiological Human Conference (VPH 2018), September 5-7, 2018, Zaragoza, Spain. Abstract @ https://simtk.org/svn/kneehub/doc/vph2018.pdf. Accessed on May 15, 2019.
5. Reproducibility in modeling and simulation of the knee: academic, regulatory, and industry perspectives, Scientific Workshop, 2019 Annual Meeting of the Orthopaedic Research Society, February 2-5, 2019, Austin, TX. Workshop handouts @ https://www.ors.org/wp-content/uploads/2019/03/Reproducibility-Knee-Compiled-FINAL.pdf. Accessed on May 15, 2019.